## Sheet1
Activity Identifier | Activity Description | Dependence | Optimistic days | Most likely days | Pessimistic days | Time Expected days
A | Review Final Application Design | - | 1 | 2 | 4 | 2
B | Review Architecture and Design | A | 2 | 4 | 7 | 4
C | Initialize Front End Development | B | 5 | 8 | 10 | 3
D | Home Screen Implementation | A,B | 7 | 9 | 12 | 8
E | Setting Implementation | A,B | 6 | 7 | 11 | 8
F | Time v Graph Implementation | A,B | 14 | 16 | 18 | 6
G | Available Time Implementation | A,B | 5 | 7 | 9 | 5
H | API Sauce integration | B | 2 | 3 | 5 | 2
I | Design and Logo | A | 3 | 5 | 8 | 2
J | Stack Navigations | D,E,F,G | 6 | 8 | 10 | 5
K | Expo Build | J | 3 | 5 | 7 | 2
L | Initialize Backend Development | B | 5 | 8 | 10 | 3
M | Database Management | L | 7 | 9 | 11 | 6
N | REST API | M | 8 | 11 | 13 | 7
O | Security and Token | M, N | 6 | 9 | 12 | 7
P | HTTPS session | O | 7 | 9 | 11 | 7
Q | Configure Google Cloud SDK | N, P | 8 | 10 | 13 | 9
R | ERD - SQL Tables | M | 6 | 8 | 10 | 8
S | Backend and Cloud Configuration | Q, N, O | 5 | 7 | 9 | 7
T | API Handlers and Integration | S | 6 | 8 | 11 | 8
U | Backend Running in Cloud | L,M,N,O,P,Q,S,T | 5 | 8 | 12 | 3
V | Application Testing | K,U | 6 | 8 | 10 | 9
W | Defect Reports | V | 4 | 7 | 9 | 2
X | Defect Fixes | W | 6 | 9 | 11 | 4
Y | Release Version 1.0 | X | 1 | 3 | 5 | 2